## Sheet1
Risk Register
Risk ID | Risks | Current Risk (1-5) |  |  | Status | Owner | Raised | Mitigation Strategies | Residual Risk (1-5)
|  | Likelihood | Impact | Severity |  |  |  |  | Likelihood | Impact | Severity
R-01 | System Complexity | 4 | 4 | 4 | Resolved | Team 19 | 2017-10-12 | * divide system into manageable components | 2 | 4 | 3
R-02 | Level of Demand for Project | 3 | 2 | 3 | Open | Team 19 | 2017-11-10 | * gauge demand with user surveys | 3 | 2 | 3
R-03 | Sufficient Tools/Resources | 2 | 4 | 3 | Open | Team 19 | 2018-01-01 | * research and test necessary functionality | 1 | 4 | 3
R-04 | Development Time | 3 | 3 | 3 | Open | Team 19 | 2018-01-22 | * create schedule to ensure steady progress | 2 | 3 | 3
R-05 | Quality of AI | 2 | 4 | 3 | Open | Team 19 | 2018-01-30 | * adjust AI as much as possible * collect user feedback | 2 | 4 | 3
R-06 | Quality of UI | 2 | 3 | 2 | Open | Team 19 | 2018-01-30 | * collect user feedback and adjust accordingly | 2 | 3 | 2
R-07 | Number of Modules | 4 | 2 | 2 | Open | Team 19 | 2018-02-02 | * focus on most important modules | 4 | 2 | 2
R-08 | Accessibility of Product | 2 | 3 | 2 | Open | Team 19 | 2018-02-06 | * collect user feedback * create for ease of use | 1 | 3 | 2
R-09 | Budget Constraints | 2 | 2 | 2 | Open | Team 19 | 2018-02-09 | * allocate resources and allow room for adjustment | 1 | 2 | 1
R-10 | Team Health | 2 | 5 | 4 | Resolved | Team 19 | 2018-02-09 | * encourage communication * provide support | 1 | 5 | 3